## Slide 1: No Estimates at Scale in the US Federal Government
Adam Parker

## Slide 2
What is No Estimates?

## Slide 3: Our Product Team
Big Sillies
Bits Please
Faux Pa’s
PO
SM
SM
SM
Teams work from single product backlog
Adds product-level ceremonies of Refinement, Planning and Retrospective

## Slide 4: Switching to Kanban
What drove us to make this decision?
As April 2018 release approaches, “dark” work emerged

## Slide 5: Before switching to Kanban
Product-level sprint board
Integration work board
Boards were separated in the hallway by a door to one of the EVE-MOD team rooms

## Slide 6: Post-workshop EVE-MOD Kanban
after
Product-level sprint board
Product-level Kanban board
before

## Slide 7: Experimenting with Refinement
Teams were looking to improve Refinement before Kanban

## Slide 8: Experimenting with Refinement
Joe Hunt, a Faux Pa’s developer, had been questioning the value of our refinement prior to Kanban.
After Kanban workshop, working committees were formed to address open items. Joe joined the Pointing committee.
First experiment: T-shirt sizing replaces story points.
excella.com | @excellaco
T-Shirt sizing fails fast, inspiring a new experiment.

## Slide 9: The June 13, 2018 Slack post
Problem Definition:
The problem with our pointing with t-shirt sizes is that our velocity is more or less a guess and we can’t forecast with confidence.
Hypothesis:
Replacing pointing with this new discussion framework will:
improve the quality of our ticket refinement discussions
measure velocity and make forecasts using PBIs and cycle time.
Proposed Solution:
Remove pointing. It’s a low value activity for us.
Monitor and plan work using cycle time & throughput measurements
Introduce a new ticket discussion framework in lieu of t-shirt sizes to drive discussion.
excella.com | @excellaco
Actual post

## Slide 10: The “No Pointing” Experiment
Problem Definition
The problem with our pointing with t-shirt sizes is that our velocity is more or less a guess and we can’t forecast with confidence.
excella.com | @excellaco

## Slide 11: The “No Pointing” Experiment
Proposed Solution
Remove pointing. It’s a low value activity for us.
Monitor and plan work using cycle time & throughput measurements.
Introduce a new ticket discussion framework in lieu of t-shirt sizes to drive discussion.
excella.com | @excellaco

## Slide 12: The “No Pointing” Experiment
Hypothesis
Replacing pointing with this new discussion framework will:
  Improve the quality of our ticket refinement discussions
  Measure velocity and make forecasts using PBIs and cycle time.
excella.com | @excellaco

## Slide 13: Discussion Cards introduced June 20, 2018
excella.com | @excellaco
Notes: Methods to encourage discussion and communication from the “3 Cs” of Story Writing

## Slide 14: Reporting in Sprints While in Kanban
To keep it simple for clients and partners, we continued to report out like we had in Scrum.
Calculating “sprint” velocity = # of items completed every two weeks (throughput) x 3 (historical average size of work items)
  For example:
    Three teams completed 27 PBIs over prior two weeks
    27 x 3 = 81 point reported as velocity at Sprint Review

## Slide 15: Inspect & Adapt is Our Brand
Return to Scrum: December 26, 2018
Return to Pointing: July 10, 2019

## Slide 16: Returning to Scrum Happens Quickly
excella.com | @excellaco
In November 2018, Big Sillies decided to approach Sprint 69 with a “Scrum Mindset”
  Create a sprint backlog
  Size work (aka pointing)
  Sprint confidence (daily)
Big Sillies visualization of Sprint 68 Team Retro notes from November 10, 2018.
EVE-MOD returns to Scrum on December 26, 2018

## Slide 17: Pointing Makes a Comeback Slowly
excella.com | @excellaco
Exiting the Sprint 85’s Overall Retro
Exiting a Sprint 75 Team Retro
EVE-MOD returns to Pointing on July 10, 2019

## Slide 18: Lessons Learned
Refinement and planning without estimates works.
Importance of splitting large work items into digestible pieces.
Power of adapting to the changes around us.
excella.com | @excellaco

## Slide 19: No Estimates worked for us because we had…
Stable team composition
Culture of learning and experimentation
Strong domain and technology knowledge
excella.com | @excellaco